## IMS - Risk Assessment
Risks |  |  | Initial Risk Level |  |  | Response |  | Final Review
Risk ID | Cause | Effect | Likelihood | Severity | Overall Risk Level | Strategy | Control Measures
1 | Minimum Viable Product not delivered | Developer is still undergoing training and has a limited programming experience. The code may not execute desired functions. Therefore unable to deliver an MVP. | 3 | 5 | 15 | Mitigate | Developer should use the courseware and the trainers help if any issues arise.
2 | Product does not meet the minimum requirments | Not reading the project specification thoroughly and not prioritising the feautures to deliver the MVP. | 1 | 5 | 5 | Mitigate | Highlight the main MVP user stories, and ensure the project spec is analysed and used for guidance.
| Requests blocked by CDRS | CRUD functionality | 4 | 5 | 20 | Mitigate | Add permission to enable cross origin requests on the API's controller class, include error response.
3 | Poor time management | Time management was a big risk highlighted during last project, as the project presentation was done last min, documentation marks are important | 3 | 5 | 15 | Mitigate | Use the Jira board as a structure and follow the time management plan set out. Highlight progress tracking.
4 | Loss of Wifi connection | Loss of internet can reduce productivity, as the project requires version control history, the API tools also require internet access. | 3 | 5 | 15 | Avoid | Find a place with stable connection and conduct work for the week at this location to avoid the possibility of a connection loss all together.
5 | Unplanned absence | Absence due to unforseen circumstances such as illness, could prevent the completion of the project | 2 | 4 | 8 | Accept | Absence due to unforseen illness are criticial and should be reported to the academy.
6 | Hardware Failure | Hardware failure can occur as a result of many reasons, and can have detrimental effects on the comppletion of the project as a result of data loss.. | 4 | 5 | 20 | Mitigate | Ensure laptop is charged appropriately, and shut off the lapotp approriately after work is saved remotely and locally. Also ensure work is pushed regularly keeping a good version control history on Github.
7 | Product fails to meet 80% testing coverage | Testing proved to be challenging in my last project, as I had put in more time than allocated, causing my project presentation to be rushed. Debugging can slow down progress and lead to low testing coverage. | 3 | 5 | 15 | Mitigate | Ensure Jira board is used to measure time allocated, and request support from trainer when debugging.
8 | Extreme Weather Warning - Heatwave | Extreme weather conditions can effect health, and lead to poor productivity. | 1 | 5 | 5 | Mitigate | Ensure to take regular breaks, to avoid exhaustion. Make sure to drink enough water to avoid dehydration, and have a fan nearby if weather is hot.

## Risk Matrix
Severity | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Likelihood